## Sheet1
WBS ID | Task Name | Crash Duration (Days) | Standard Duration (Days) | Stretch Duration (Days) | Crash Cost ($) | Standard Cost ($) | Stretch Cost ($)
1.3.1.1 | Shopping Cart Integration | 3 | 6 | 8 | 3000 | 2000 | 1200
1.3.1.2 | Product Upload Process | 2 | 5 | 7 | 2400 | 1500 | 900
1.3.1.3 | Payment Gateway Setup | 3 | 6 | 9 | 3200 | 2100 | 1300
1.3.2.1 | Homepage & Sign-Up Page | 2 | 5 | 7 | 2600 | 1600 | 1000