## Sheet1
WBS ID | Task Name | Duration (Days) | Early Start (ES) | Early Finish (EF) | Late Start (LS) | Late Finish (LF) | Float (Slack) | Critical Path
1.3.1.1 | Shopping Cart Integration | 6 | 1 | 6 | 1 | 6 | 0 | Critical
1.3.1.2 | Product Upload Process | 5 | 1 | 5 | 8 | 12 | 3
1.3.1.3 | Payment Gateway Setup | 6 | 7 | 12 | 7 | 12 | 0 | Critical
1.3.2.1 | Homepage & Sign-Up Page | 5 | 1 | 5 | 8 | 12 | 3