## Sheet1
Predecessor ID | Predecessor Task | Dependent ID | Dependent Task
1.1.2 | Define Website Requirements | 1.2.1 | Design Site Architecture
1.2.1 | Design Site Architecture | 1.3.1 | Build Online Pro Shop Functionality
1.3.1 | Build Online Pro Shop Functionality | 1.6.3 | Perform Final Updates and Approvals
1.3.2 | Develop Other Core Pages | 1.4.2 | Launch Campaign for Website Rollout
1.5.1 | Set Budget and Approval Cycle | 1.5.2 | Track Project Costs and Variance
1.1.4 | Review Budget and Timeline Assumptions | 1.5.1 | Set Budget and Approval Cycle
1.6.1 | Conduct Internal QA & Testing | 1.6.4 | Official Handoff to GGG Staff
1.6.2 | Collect Stakeholder Feedback | 1.6.3 | Perform Final Updates and Approvals