## Sheet1
WBS ID | Task Name | Responsible Party
1.0 | GGG Website Rollout Project | Jamie Edwards
1.1 | Requirements & Planning | Jamie Edwards
1.1.1 | Conduct Stakeholder Interviews | Jamie Edwards
1.1.2 | Define Website Requirements | Tony Stark
1.1.3 | Draft Requirements Document for Approval | Jamie Edwards
1.1.4 | Review Budget and Timeline Assumptions | Bruce Wayne
1.2 | Technical Design | Tony Stark
1.2.1 | Design Site Architecture | Tony Stark
1.2.1.1 | Define Information Hierarchy | Tony Stark
1.2.1.2 | Create Wireframes | Tony Stark
1.2.2 | Plan Backend Infrastructure | Tony Stark
1.2.2.1 | Identify Hosting Requirements | Tony Stark
1.2.2.2 | Build Dev Environment | Tony Stark
1.3 | Development | Tony Stark
1.3.1 | Build Online Pro Shop Functionality | Tony Stark
1.3.1.1 | Shopping Cart Integration | Tony Stark
1.3.1.2 | Product Upload Process | Tony Stark
1.3.1.3 | Payment Gateway Setup | Tony Stark
1.3.2 | Develop Other Core Pages | Tony Stark
1.3.2.1 | Homepage, Facility Info, Class Sign-Ups | Tony Stark
1.4 | Marketing & Launch | MJ Watson
1.4.1 | Design Marketing Strategy | MJ Watson
1.4.2 | Launch Campaign for Website Rollout | MJ Watson
1.4.2.1 | Email Newsletter | MJ Watson
1.4.2.2 | Social Media Announcements | MJ Watson
1.4.2.3 | Member Referral Bonus | MJ Watson
1.5 | Finance & Reporting | Bruce Wayne
1.5.1 | Set Budget and Approval Cycle | Bruce Wayne
1.5.2 | Track Project Costs and Variance | Bruce Wayne
1.5.3 | Final Cost Report & Analysis | Bruce Wayne
1.6 | Review & Handoff | Jamie Edwards
1.6.1 | Conduct Internal QA & Testing | Jamie Edwards
1.6.2 | Collect Stakeholder Feedback | Jamie Edwards
1.6.3 | Perform Final Updates and Approvals | Jamie Edwards
1.6.4 | Official Handoff to GGG Staff | Jamie Edwards